## WBS
과제명 | 전통주 오프라인 매장 오픈을 위한 정보와 고객 구매 서비스 제안 | [5 empty] | 일정관리담당자 |  |  | 김세화
과제책임자 | 이종수 | 과제기간 | 2022.11.28 ~ 2022.12.23 |  |  |  | 최종작성일 |  | 2022.12.07 | 기간경과율 |  | 80%
WBS | 작업 이름 | 기간 | 시작 날짜 | 예상 완료 날짜 | 실제 완료 날짜 | 계획율 | 완료율 | 진척율 | 계획진척율 | 담당자 | Task연계성 | 산출물
1 | 전통주 오프라인 매장 오픈을 위한 정보와 고객 구매 서비스 제안
1.1 | 과제 계획 | 12 | 2022-11-14 | 2022-11-25 | 2022-12-02 | 100% | 100% | 100%
1.1.1 | 과제 계획 수립 | 12 | 2022-11-14 | 2022-11-25 | 2022-11-25 | 100% | 100% | 100% |  |  |  | 과제계획서
1.1.2 | WBS 수립 | 2 | 2022-11-28 | 2022-11-29 | 2022-12-02 | 100% | 100% | 100% |  |  |  | WBS
1.2 | 분석 (보완) | 3 | 2022-11-28 | 2022-11-30 | 2022-11-30 | 100% | 100% | 100%
1.2.1 | 전통주 검색어트렌드, 시장 분석 | 3 | 2022-11-28 | 2022-11-30 | 2022-11-30 | 100% | 100% | 100%
1.2.2 | 크롤링 데이터 분석 | 2 | 2022-11-29 | 2022-11-30 | 2022-11-30 | 100% | 100% | 100%
1.2.3 | 감성분석 방법 확인 | 2 | 2022-11-29 | 2022-11-30 | 2022-11-30 | 100% | 100% | 100%
1.3 | 설계/구현/테스트 | 19 | 2022-11-28 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.1 | 알고리즘 설계 | 19 | 2022-11-28 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.1.1 | 감성분석 | 10 | 2022-11-28 | 2022-12-07 | 2022-12-07 | 100% | 100% | 100% |  |  |  |  | LM용일본어g2p생성_일본어숫자전처리_사용자사전
1.3.1.2 | 카테고리별 단어추출 | 6 | 2022-12-02 | 2022-12-07 | 2022-12-07 | 100% | 100% | 100% |  |  |  |  | 한국어1000시간,일본어360시간
1.3.1.3 | 관련단어 정리 | 6 | 2022-12-02 | 2022-12-07 | 2022-12-07 | 100% | 100% | 100%
1.3.1.4 | 데이터 전처리(불용어 제거) | 6 | 2022-12-02 | 2022-12-07 | 2022-12-07 | 100% | 100% | 100%
1.3.1.5 | 해시태그 | 9 | 2022-12-08 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.1.6 | 자동문장 완성 | 9 | 2022-12-08 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.2 | 마켓 포지셔닝 맵 구현 | 19 | 2022-11-28 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.2.1 | 카테고리 설정 및 정리 | 10 | 2022-11-28 | 2022-12-07 | 2022-12-07 | 100% | 100% | 100%
1.3.2.2 | 정제한 데이터에 적용 및 분류 | 9 | 2022-12-08 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.2.3 | 마켓 포지셔닝 맵 작성 | 9 | 2022-12-08 | 2022-12-16 | 2022-12-16 | 100% | 100% | 100%
1.3.3 | 웹 화면설계서 & 레이아웃개발 | 3 | 2022-12-19 | 2022-12-21 |  | 100% | 100% | 100%
1.4 | 동료검토 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100%
1.4.1 | 기획서 | 25 | 2022-11-28 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 기획서
1.4.2 | WBS | 25 | 2022-11-28 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | WBS
1.4.3 | 기획 PPT | 6 | 2022-11-30 | 2022-12-05 | 2022-12-05 | 100% | 100% | 100% |  |  |  | 기획 PPT
1.4.4 | 비즈니스 모델 계획서 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 비즈니스 모델 계획서
1.4.5 | 알고리즘 구축 계획서 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 알고리즘 구축 계획서
1.4.6 | 요구사항정의서 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 요구사항정의서
1.4.7 | 빅데이터분석 정의서 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 빅데이터분석 정의서
1.4.8 | 화면설계서 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 화면설계서
1.4.9 | 테이블 명세서 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 테이블 명세서
1.4.10 | 소스검토 | 18 | 2022-12-05 | 2022-12-22 |  | 100% | 100% | 100% |  |  |  | 소스검토

## Sheet1
Compatibility Report for 2.WBS.xls
Run on 2022-11-29 9:42
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 25 | Excel 97-2003